## Sheet1
| Serial Number | Test Description | Entry Criteria | Exit Criteria | Expected Outcome | Actual Outcome | Date | Pass/Fail
story 1 | A01 | Check window minimize button functionality | click minimize button | window size becomes reduced | webpage should be minimised | webpage was minimised | 2017-10-12 | Pass
| A02 | Check Close button functionality | Click close button | window is closed | Webpage should be closed off | webpage was closed off | 2017-10-12 | Pass
| A03 | Check if window is re-sizable | click and drag the corner of the screen to manually resize | window resized | webpage should rescale to the size of the window | webpage rescaled to the size of the window | 2017-10-12 | Pass
| A04 | Check scroll bar functionality for window | spin scroll wheel or drag scroll bar | page scrolls down | webpage scroll functional | webpage scrolled down | 2017-10-12 | Pass
story 2 | B01 | All fields on page (e.g. text box, radio options, dropdown lists) should be aligned properly | open page | page opened | fields load in the correct locations and are aligned | all fields loaded in aligned | 2017-10-12 | Pass
| B02 | Enough space should be provided between field labels, columns, rows, error messages etc. | open page | page opened | fields load in correct locations and dont overlap | fields were loaded in correctly | 2017-10-12 | Pass
| B03 | Upon click of any input text field, mouse arrow pointer should get changed to cursor | click input field | pointer is now a cursor | pointer is now a cursor in sign-in fields | pointer is a cursor on sign-in fields | 2017-10-12 | Pass
| B04 | Check if correct data is getting saved in database upon successful page submit | click submit button | displays message saying account creation was successful | displays message thank you for registering, return to home page | displays message thank you for registering, return to home page | 2017-10-12 | Pass
| B05 | No duplicate user names in the database | click enter on user creation (user name is a duplicate) | error message displays user name is already taken | error message displaying username already exists, asks user to try again | error message displaying username already exists, asks user to try again | 2017-10-12 | Pass
story 3 | C01 | All fields on page (e.g. text box, radio options, dropdown lists) should be aligned properly | open page | page opened | fields load in the correct locations and are aligned | all fields loaded in aligned | 2017-10-12 | Pass
| C02 | Enough space should be provided between field labels, columns, rows, error messages etc. | open page | page opened | fields load in correct locations and dont overlap | fields were loaded in correctly | 2017-10-12 | Pass
| C03 | Upon click of any input text field, mouse arrow pointer should get changed to cursor | click input field | pointer is now a cursor | pointer is now a cursor for input fields | pointer is a cursor for input fields | 2017-10-12 | Pass
| C04 | Data corresponds with user’s info in the database | user clicks login enter button | user is directed to the home page in their account | user is directed to the information page in their account | user is directed to the information page in their account | 2017-10-12 | Pass
| C05 | Sensitive fields like passwords should not have auto complete enabled | user begins to enter details in inout field | user is left to complete passwords themselves | password auto-complete is not be enabled, so that cache data is not stored | password auto-complete is not enabled | 2017-10-12 | Pass
story 4 | D01 | All fields on page (e.g. text box, radio options, dropdown lists) should be aligned properly | open page | page opened | fields load in the correct locations and are aligned | all fields loaded in aligned | 2017-10-12 | Pass
| D02 | Enough space should be provided between field labels, columns, rows, error messages etc. | open page | page opened | fields load in correct locations and dont overlap | fields were loaded in correctly | 2017-10-12 | Pass
| D03 | Upon click of any input text field, mouse arrow pointer should get changed to cursor | click input field | pointer is now a cursor | pointer is now a cursor for input fields | pointer is a cursor for input fields | 2017-10-12 | Pass
| D04 | Cannot be accessed from a standard user account | open page | Admin creation is not on the bootstrap | Standard user isn't able to access admin page | Standard user isn't able to access admin page | 2017-10-13 | Pass
| D05 | Check if correct data is getting saved in database upon successful page submit | click enter on admin creation | message displays that admin was successfully created | message displays that admin creation was successful | message displays that admin creation was successful | 2017-10-13 | Pass
| D06 | Admin account can only use permissions given to it |  |  | Only can add or edit, if the admin has permissions to do so | Only can add or edit, if the admin has permissions to do so | 2017-10-13 | Pass
| D07 | Test password security and password policy enforcement | admin being created uses password that doesn’t confine to the password agreement | error message displayed under password field | error message displayed after incorrect password entered | error message displayed after incorrect password entered | 2017-10-13 | Pass
story 5 | E01 | Website emails the users’ chosen email address with a randomly generated new password | click enter on forgotten password button | user opens their email address | The chosen email account should receive an email from Smart City | Email is received | 2017-11-01 | Pass
| E02 | New generated password once entered with corresponding username overwrites old password when logging in | click enter on forgotten password button | displays message that password has been emailed to corresponding address | The chosen email account should receive an email from Smart City | Email is received, the password reset is complete | 2017-11-01 | Pass
story 6 | F01 | Database stores the change of the user type in the users’ personal information | user selects a different user type option | new user type displayed on user personal information page | New user type is chosen and displayed on the user's personal profile | User type is displayed on the user's personal profile | 2017-10-13 | Pass
| F02 | Corresponding artifacts to the users’ type are displayed on the page if the user type has changed | user selects a different user type option | map displays new artefact types for user to browse | Display artefact types for the user to browse | Display artefact types for the user to browse | 2017-10-13 | Pass
| F03 | Check if page load time is within acceptable range | user selects a different user type option | page updated | Page performance should be of high standards | Page performance is of high standards (Network test-Lighthouse plugin) | 2017-10-13 | Pass
| F04 | Check response time for any action under light, normal, moderate and heavy load conditions | user selects a different user type option (at different stress levels) | page updated under stress | Page performs at high standard at different levels of stress | Page performed at high stand on different stress levels | 2017-10-13 | Pass
| F05 | Check database query execution time | user selects a different user type option | database updated | Page loads information in a timely manner | Page loads information in a timely manner | 2017-10-13 | Pass
| F06 | Check if buttons work correctly | user presses combobox and radiobutton | combobox drops down the 3 different options, radio buttons are all functional | Takes user to relevant category | Takes user to relevant category | 2017-10-13 | Pass
story 7 | G01 | Check if data is committed to database only when the operation is successfully completed | admin presses enter button to add artefact | displays message that artefact has been added to the database | Data is added to database successfully | Data is added to database successfully | 2017-10-13 | Pass
| G02 | Required table indexes should be created | admin presses enter button to add artefact | database updated | Data is shown in relevant table | Data is shown in relevant table | 2017-10-13 | Pass
story8 | H01 | Information being added overrides the original corresponding data in the database | admin presses enter button to edit artefact | database updated | Updated data is stored in database | Updated data is stored in database | 2017-10-13 | Pass
| H02 | No new values or information can be set as null | admin presses enter button to edit artefact | error message displayed states that artefact cannot be set as null | Error when a null value is detected and user tries to save | Error when a null value is detected and user tries to save | 2017-10-13 | Pass
| H03 | artefact detail fields have the correct type of data in them | admin presses enter button to edit artefact | error message displayed states that artefact cannot be updated, data type incorrect | Error displayed if wrong data type entered | No error for some fields if wrong data type entered | 2017-10-13 | Fail
story 9 | I01 | Information in the index about deleted item is removed | admin presses enter button to edit artefact | database updated | Item is deleted and no longer in database | Item is deleted and no longer in database | 2017-10-13 | Pass
| I02 | Tables and columns containing artifact are updated and done contain the deleted artifact | admin presses enter button to edit artefact | database updated | Tables don't show deleted item | Tables don't show deleted item | 2017-10-13 | Pass
story 10 | J01 | Check for stress testing of web page | user attempts to update information page under stress | information page updated | Page loads relevant information | Page loads relevant information | 2017-10-13 | Pass
| J02 | Check database query execution time | user updates information page | database updated | Page loads information in a timely manner | Page loads information in a timely manner | 2017-10-13 | Pass
| J03 | Check if page load time is within acceptable range | user updates information page | information page updated | Page loads information in a timely manner | Page loads information in a timely manner | 2017-10-13 | Pass
| J04 | Check if default window size is correct | open page | page opened | Default page size is correct | Default page size is correct | 2017-10-13 | Pass
| J05 | Check window minimise funtionality | click minimize button | page minimised | Page minimises correctly | Page minimises correctly | 2017-10-13 | Pass
| J06 | Check window maximise funtionality | click maximise button | page maximised | Page maximises correctly | Page maximises correctly | 2017-10-13 | Pass
| J07 | Check window close funtionality | Click close button | page closed | Page closes correctly | Page closes correctly | 2017-10-13 | Pass
| J08 | Check if window is re-sizable | click and drag the corner of the screen to manually resize | page resized from user | Window is resizeable | Window is resizeable | 2017-10-13 | Pass
| J09 | Check scroll bar functionality for windows | click and drag scroll bar | window scrolls up and down | Page scrolls correctly | Page scrolls correctly | 2017-10-13 | Pass
story 11 | K01 | Only categories related to the users’ type are displayed | open information page | page opened | Page only shows categories related to user type | Page shows categories related to user type | 2017-10-13 | Pass
story 14 | L01 | button for log out signs out the user, database commites data that user is currently logged out | user clicks sign out button | database sets the use as logged out | User is logged out | User is logged out | 2017-10-13 | Pass
story 15 | M01 | site access to site features is nullified until user signs in again | user tyies to access the site features | error message displayed stating they need to be signed in | User isn't able to access certain pages unless signed in | User isn't able to access certain pages unless signed in | 2017-10-13 | Pass
Spint 2
story 12 | N01 | details on specific item are opened on page | button widget is clicked for the specific item | Details of the item are displayed below the photo of the item | Details on the item are displayed below is description pic | details were listed in the correct location | 2017-10-31 | Pass
| N02 | correct details on the specific data are pulled from internet or database | button widget is clicked for the specific item | the data on this page is accurate | Details on the item correspond to details listed on google | details listed were accurate and correctly pulled from the database | 2017-10-31 | Pass
story 13 | O01 | Displays the selected artefact | open information page | different artefacts displayed | map displays the selected item | Item was displayed clearly on the map | 2017-10-31 | Pass
| O02 | Drag on map to travel across the map | open information page | page opened | user can traverse map through click and drag | click and drag functionality was successful | 2017-10-31 | Pass
| O03 | Check scroll wheel for zoom in and out | scroll in and out over map | map zooms in and out | user can scroll in and out to increase their range of vision | zoom in and out functionality was successful | 2017-10-31 | Pass
story 16 | P01 | search bar has predictive text for artefacts currectly logged to the database | user types into the search bar | user hits the enter key | Predicts POI as you type | Doesn't predict POI as you type | 2017-10-31 | Pass
| P02 | words are contained to the input field at all times (Font fits to the bounds of the field) | user types into the search bar | user finished typing in their specified location | Words remain in input text box | Words remain in input text box | 2017-10-31 | Pass
| P03 | search bar is correctly located to the top left confines of the bootstrap | user types into the search bar | user finished typing in their specified location | Search bar is located around top left corner | Search bar is located around top left corner | 2017-10-31 | Pass
| P04 | pointer is converted to a cursor when user clicks on the input field | user clicks on searcg bar | user finished typing in their specified location | Cursor is displayed flashing waiting for input | Cursor is displayed flashing waiting for input | 2017-10-31 | Pass
story 17 | Q01 | map only takes up a marginal portion of the screen | user enters specified item | user looks at map loaded on the page | Map is displayed allowing room for item details | Map is displayed allowing room for item details | 2017-10-31 | Pass
| Q02 | map pulls the correct coordinates from the database | user enters specified item | user looks at map loaded on the page | Map displays correct location of item | Map displays correct location of item | 2017-10-31 | Pass
| Q03 | functional components for the map work (zoom in, out, click-drag to change position) | user enters specified item | user can zoom in, out etc. | Able to zoom in and out and drag map around | Able to zoom in and out and drag map around | 2017-10-31 | Pass
story 18 | R01 | user profile correctly pulls info on the user from the database | user opens profile page | user's data is displayed | page correctly shows user information | page correctly shows user information | 2017-10-31 | Pass
| R02 | user can edit data on that page by clicking the edit button (data is then commited to the database and overwrites information to the changed input field | user clicks edit button | user presses enter button to commit this change | user able to edit information and data is submitted to database | functionality not complete | 2017-10-31 | Fail
| R03 | input fields for editing and display fields for plaintext are spaced evenly and words do not overlap | user opens profile page | user's data is displayed | evenly spaced and words do not overlap | evenly spaced and words do not overlap | 2017-10-31 | Pass
story 19 | S01 | new data related to users details can overwrite old data | user presses enter button | old data is overwritten | The user can change their user data | functionality not complete | 2017-10-31 | Fail
| S02 | no fields can be set as null | user presses enter button on empty field | error message is displayed saying "no field can be set as null" | The user cannot set these fields to null | functionality not complete | 2017-10-31 | Fail
story 20 | T01 | user clicks account deletion button to delete account | user opens their profile page | user clicks account deletion button | The user can delete their account via a button press | functionality not complete | 2017-10-31 | Fail
story 21 | U01 | contacts page correctly displays information relevant to the certain admin next to their ID picture | user opens contacts page | user loads contacts page | page correctly shows contact information | page correctly shows contact information | 2017-10-31 | Pass
| U02 | no labels are overlapping or hidden behind the admin's png | user opens contact page | user loads contacts page | no labels are overlapping or hidden behind the admin's png | no labels are overlapping or hidden behind the admin's png | 2017-10-31 | Pass
story 22 | V01 | all label are loaded in correctly | user opens help page | user loads in help page | help page loads for the user and labels are loaded correctly | help page loads for the user and labels are loaded correctly | 2017-10-31 | Pass
| V02 | all labels are loaded in correctly and don’t overlap | user opens help page | user loads in help page | help page loads for the user and labels don't overlap | help page loads for the user and labels don't overlap | 2017-10-31 | Pass
story 24 | W01 | link on items page for favourites page portals users to the correct location | user clicks hyperlink for favourites pages | portalled to favourites page | Links in favourites takes user to correct item page | Links in favourites takes user to correct item page | 2017-10-31 | Pass
| W02 | button to favourite and item correctly commits item to the database in terms of favourites | user clicks button to favourite item | data is commited to the database | User id and item id stored in database | User id and item id stored in database | 2017-10-31 | Pass
| W03 | button on bootstrap correctly takes users to the page where it shows the bookmarked items | user clicks favourites page button | user is portalled to favourotes page | Favourites button takes user to favourites page | Favourites button takes user to favourites page | 2017-10-31 | Pass
story 25 | X01 | button to the review page portals user to the review page | user clicks review page button | user is portalled to the review page | The review page is accessible from the item page | The user can write reviews on the item page | 2017-10-31 | Pass
| X02 | combo boxes and input fields load correctly | user clicks review page button | user loads in review page | The input fields all function correctly | The input fields all function correctly | 2017-10-31 | Pass
| X03 | selecting a 0-5 value for the combo box commits the data to the database, thus updating the items review value | user selects combo box value | data is commited to the database | The items average review score will be displayed | functionality not complete | 2017-10-31 | Fail
| X04 | comments placed by user are correctly committed to the database, then displayed as a comment underneath review item | user clicks enter once a review is posted in the input field | data is commited to the database | Geo-location data is correctly collected from the user | functionality not complete | 2017-10-31 | Fail
story 26 | Y01 | geo-location data is collected from the user so distance to the item can be calculated | user has allowed site to access location | data is displayed on the item page | Pindrop for selected item has the correct coordinates | Pindrop for selected item has the correct coordinates | 2017-10-31 | Pass
| Y02 | pindrop for selected item has the correct coordinates | user navigates to item page | user loads in item page | Correct and accurate distance calculations | functionality not complete | 2017-10-31 | Fail